## Slide 1: Final evaluation of the effectiveness of the programm „Local development and poverty reduction“
Researchers: Sandra Haugas, Aet Annist, Elisabeth Kendrali, Anni Kurmiste, Miriam Lehari, Katre Pall, Moonika Raja, Gertha Teidla-Kunitsõn, Maarja Tinn, Mariliis Öeren

## Slide 2
Program „Local development and poverty reduction"
The program was part of the European Economic Area (EEA) and Norwegian Financial Mechanisms 2014–2021.
The program was implemented between 09.2019 and 04.2024.
Program operator: The Department of Foreign Financing of Ministry of Social Affairs
Implementing authority: Grants Implementing Department of State Shared Service Centre
Ministry of Education and Research, Ministry of Justice and Ministry of Culture were involved.
3 Partner Organizations: Norwegian Public Health Institute, the Norwegian Directorate of Health and the Norwegian Directorate of Cultural Heritage.
Goal of the program: to increase the socio-economic cohesion of society.

## Slide 3
Measures
 | Expected outcome
Measure 1 | Enhanced wellbeing of children and youth
Measure 2 | Reduced domestic and gender-based violence and gender inequalities
Measure 3 | Improved prevention and reduced inequalities in health
Measure 4 | Enhanced status of Cultural Heritage

## Slide 4
Research method
Intervention logic analysis
  Comparing planned and actual intervention logics
Sub-methods:
  Indicator analysis
  Document analysis
  Analysis of individual and focus group interviews

## Slide 5
Key findings and recommendations

## Slide 6
Key findings (program level)
Most target levels of the output and outcome indicators set in the projects were achieved. Cultural heritage measure was the one with the least target levels achieved.
Far-reaching conclusions about the effectiveness of the program cannot, however, be drawn as the accuracy and appropriateness of setting the outcome indicators was somewhat questionable sometimes.
Potentially characteristic of large programs combining several fields, the risk of complex implementation was realized in the "Local Development and Poverty Reduction" program, which was mainly expressed in long delays.
Different areas in the program were not sufficiently integrated, and therefore the potential of integration to achieve greater social impact was not used.
While the program was technically very competently managed, insufficient attention was paid to the substantive coordination of the process.
Even though all the topics that the program focused on were important and acute, in certain cases it remained unclear why such a selection of topics was formed. In addition, it was not always transparent how the proportions were formed in the funding of different areas.

## Slide 7
Recommendations (program level)
Ensure that accurate and relevant output and outcome indicators are defined in the projects.
Consider making the use of program theory mandatory in the project planning stage.
To realize the potential for integration of large and multi-disciplinary programs, it is important to pay attention to the substantive coordination of the various areas and activities of the program, for which the positions of content coordinators at the measure and program level should be created.
A critically important prerequisite for the realization of the potential to achieve a greater societal impact is also starting from one big goal, on the basis of which sub-goals, related areas and institutions/actors are established, as well as a comprehensive and systematic approach to moving towards this goal.
It is important to continue funding all the subject areas that were the focus of the program. In the future, however, it should be shown more transparently how the proportions of the financing of different areas are formed and how the selection of specific topics within the measure is formed. Also, in the future, more focus should be placed on a problem-preventive approach.

## Slide 8
Measure 1: Child and youth welfare
31 projects were implemented within this measure, including 3 pre-defined projects and 28 projects with open application rounds.
We evaluated the following projects:
„Specialised juvenile justice approach established“,
„Establishment of a renewed family mediation system“,
„Implementation of Vocational Orientation Curriculum in Pärnumaa Vocational Education and Training Centre (in partnership with Hiiumaal Vocational School)“,
„Cyber Training Programme for Youth and Youth Workers“,
„Trauma-informed counselling in educational support services“,
„Integrated services to prevent early school leaving in Võru country“.

## Slide 9
Key findings (measure 1)
Outputs and outcomes were largely achieved, activities were in line with the objective of the measure.
Focus on problem prevention and specific problems.
There could have been more focus on developing general skills.
There was insufficient focus on the challenges of the youth field.
The program laid the foundation for the establishment and better availability of several modern policy interventions in Estonia.
Linkage of projects to national reforms as one of the main factors of sustainability.
The potential of wider impact is more likely in projects where the knowledge and skills of specialists were developed, and where cooperation networks were developed.
Obstacles: long delay, limited opportunities for participation, frequent staff turnover.
Facilitators: political priority, target groups’ interest, competent coordination.

## Slide 10
Recommendations (measure 1)
Define measurable output and outcome indicators.
Target acute challenges and prioritize innovative and evidence-based interventions.
Fund projects that develop general skills and prevent problems, especially among vulnerable groups.
Involve direct beneficiaries in program and project planning.
Ensure learning opportunities for professionals and opportunities to apply what they have learned.
Support projects that maintain (and create, if necessary) cooperation networks.
Carry on financing both pre-defined projects as well as open application rounds’ projects. In the case of the former, ensure that they are closely related to national priorities.

## Slide 11
Measure 2: Gender equality
6 projects were implemented within this measure, including 2 pre-defined projects and 4 projects with open application rounds.
We evaluated the following projects:
„Strengthening the Victim Support System“,
„ Raising the Awareness of Estonian Specialists about Domestic Violence“,
„Raising the Awareness of Estonian Specialists about Domestic Violence“,
„Social Programme SPSV“,
„Awareness raising activities on domestic violence and discouraging the demand for commercial sex“.

## Slide 12
Key findings (measure 2)
The planned outputs and outcomes were largely achieved. The activities of the evaluated projects were relevant and in line with the broader objectives of the program.
Attitudes towards violence in society have become less victim-blaming, and awareness of gender-based violence has increased. However, the reduction of violent crimes is still not clearly visible.
The activities focused more on helping victims of violence and less on changing the behavior of perpetrators of violence.
The activities were not directed specifically at the Russian-speaking population or at the regions with the highest number of domestic violence crimes (Ida-Virumaa).
NGOs are valuable partners in raising awareness because they have practical knowledge of the field, the ability to train and exposure to the target group. Sustainability is hindered by the lack of resources of NGOs.
In addition to raising awareness, the main value of the first-level specialist trainings was the opportunity to develop cooperation between authorities.
Risk groups specified in the violence prevention agreement 2021-2025, including people with special needs and the elderly, were not included to the measure.

## Slide 13
Recommendations (measure 2)
Continue developing and implementing violence prevention activities systematically.
Pay much more attention than before to interventions aimed at perpetrators of violence. Develop evidence-based behavior change interventions for that matter.
Direct more violence prevention and victim assistance activities to the Russian-speaking population and to regions where family and gender-based violence occur more (mainly Ida-Virumaa).
Continue to involve and support sectoral NGOs as partners in violence prevention, victim assistance and awareness raising.
Continue with the trainings and networking events for primary care professionals. In the long term, consider including violence topics (e.g. in the field of health care) in the curricula.
Focus more on distributing the tools, including manuals, developed in the activities of the measure. Materials should be easily available in one place and cross-used between organizations.
In the future, pay special attention to and develop interventions for risk groups, including the elderly, disabled and other groups whose access to victim assistance services is difficult.

## Slide 14
Measure 3: Social and healthcare
5 projects were implemented within this measure, including 3 pre-defined projects and 8 projects with open application rounds.
We evaluated the following projects:
„Increasing physical activity of schoolchildren“,
„Development of evaluation model and handling system for chronically mentally ill patients“,
„Development and Piloting of a Methodology for the Assessment and Reduction of the Risk of Injury in the Home Environment and Supporting Activities“,
„Home Visits by Midwives During the First Years of Life“.

## Slide 15
Key findings (measure 3)
• The outputs and outcomes planned for the measure were largely achieved. The activities of the evaluated projects were relevant and in line with the broader objectives of the program.
• Achieving output indicators was sometimes misinterpreted as proof of impact. Causal relationships were presented too firmly.
• Large scale projects were very specifically oriented and only two applications were received (both received funding).
• During the interviews, different interpretations and messages about the implementation of the project were revealed by policy makers and project implementers.
• The reports do not deal with risk management in sufficient detail, so it remains unclear how the initially identified risks affected the course of the project.
• Unplanned negative or unexpected impacts were not systematically addressed in the projects (therefore, their detection and mitigation is incomplete).
• Changing the focus of the projects was possible due to flexibility, increasing the relevance of the projects.

## Slide 16
Recommendations (measure 3)
• Critically assess under which conditions one can talk about the project's effectiveness. When evaluating projects, emphasize the quality of causal analysis and clear criteria for determining effectiveness.
• Provide transparent criteria and procedures that describe the selection of topics and implementers of the projects to ensure transparency of the processes.
• In the final phase of the projects, organize a comprehensive ex-post analysis, the purpose of which is to evaluate the progress of the projects and to highlight both success factors and improvement needs, including dealing with risk management.
• Integrate a systematic approach to the assessment of unplanned negative or other unexpected effects in the implementation of projects (e.g. during the interim report).
• Consider using program theory in the planning phase of the projects to be made mandatory.
• Continue to consider flexible mechanisms that allow changing the initial focus, scope or methodology of projects in justified cases also in the later stages of the project.

## Slide 17
Measure 4: Cultural heritage
7 projects were implemented within this measure, including 1 pre-defined projects and 6 projects with open application rounds.
We evaluated the following projects:
“Historic Town Centres Revitalised Through Heritage-led Local Development“,
“Development of an historic inn in Võru at F. R. Kreutzwald str 52 into a guest house and a remote workplace”.

## Slide 18
Key findings (measure 4)
The outputs and results planned for the measure were mostly achieved.
The impact of activities on the achievement of broader goals cannot be proven.
The link of the measure to the broader program goals was indirect; local development was not sufficiently clearly defined either at the program or projects level.
Communication with Norwegian partners had an important impact.
There is no analysis of the impact of training and cooperation.
No pre- and post-intervention evaluations were conducted to assess the increase in awareness. Dissemination of information and substantial increase in awareness are not necessarily related.
In places, mainly or only individual active members of society were involved, who may or may not have the capacity to influence the intervention environment more broadly.
The intended impact of the projects was economic, environmental and social; the actual impact is primarily economic, partly also environmental.
The sustainability of projects depends on the business, political and administrative landscape, important socio-economic changes and the motivation and ability of those involved to continue.
Facilitating factors: socio-economic factors and flexibility on the part of donors. Barriers: socioeconomic and regulatory factors.

## Slide 19
Recommendations (measure 4)
Continue to support heritage conservation areas in small towns.
Analyze the impact of broader socio-economic processes on local life and the possibility of its revitalization.
When developing measures, start with the program goals, defining them, and systematically build a process clearly leading to the achievement of the goal.
Continue cooperation projects with experienced partners who are aware of involvement; at the same time, make the acquisition and practice of this knowledge more systematic.
Evaluate the acquisition of knowledge in trainings, information events and other activities of the measure. Ensure time and financial resources to flexibly make decisions about additional training/information.
Train teams on inclusive processes and support inclusive solutions at every level.
Involve managers and entire levels in training.
Stimulate the interest of relevant institutions in cooperation, offer the possibility of continued participation.
Community sustainability should be included in project sustainability assessments as a component equal to economic and financial sustainability. Develop information materials that would help applicants/project teams to assess and achieve such sustainability.
Support project teams in overcoming regulatory/administrative issues.